## Slide 1
Haav
Highly Amphibious / Autonomous Vehicle
UW–Madison
College of Engineering
A student team building an autonomous boat from the ground up.
First-principles mixed-integer linear programming
We build the model from physics up. Each constraint cuts the space of possible boats, and the optimizer finds the fastest one left. Hull resistance comes from Savitsky's planing-hull model. As we build and test, we keep updating the model and adding constraints: a hybrid of simulation and empirical data.
Engineers from across UW–Madison
Each segment of the boat is covered, and members have worked at Tesla, Northrop Grumman, Xcel Energy and Milwaukee Tool.
Industrial
optimization, composites and manufacturing
Mechanical
structures, CAD and fabrication
Electrical
power, battery and high voltage
Computer
embedded, firmware and software
Our approach
Hull
Plane well and stay light.
Hybrid planing composite hull
Shape tuned by optimization
Resistance checked in CFD first
Electric
Every watt-hour to speed.
High-voltage battery storage
Propulsion sized by the model
Propulsion and cooling co-designed
Autonomous
Manage drift and controls.
GPS, IMU and LIDAR sensing
Firmware protects the battery
Software plans the route
Timeline
Oct 25
Hull design frozen
Nov 1
Preliminary design review
Nov 10
Critical and long-lead parts are ordered
Nov 20
Mechanical and electrical design frozen
Nov 20–Dec 20
Build the hull, composite parts and any custom-milled parts
Jan 8
First float and tow test
Jan 8–30
Manufacture and assemble everything
Jan 8–30
Build likely spare parts, in parallel
Jan 31
First nautical mile
Feb 1–14
Slow drives on the water
Feb 15
Start increasing speed
Until April
Testing / Tuning
Want to help build it?
We are looking for funds, parts, advisors and people to build our BOM as we design.
bit.ly/haav
Marley Barrett, Project lead
mhbarrett@wisc.edu